MIRACLE PICTURES  /  INTERNAL OPERATING DOCUMENT

PIYE TO KIH?

META ADS OPERATING HANDBOOK

v1.1  |  19 October 2026 → Theatrical Holdover

Panduan kerja tim untuk membangun demand, mendeteksi theatrical intent, mengonversi ticket action, mengelola roadshow presale, dan mempertahankan occupancy setelah film tayang.

|  | PRINSIP UTAMA PIYE TO KIH? adalah film nasional. WOKO adalah ignition/reactivation/mobilization engine, bukan ceiling market. Paid media tidak membeli views sebagai tujuan akhir; paid membangun demand menuju kursi bioskop. |
| --- | --- |

|  | BUDGET Maximum Meta Ads envelope: Rp100.000.000. Angka ini adalah batas kemampuan belanja, bukan target yang wajib dihabiskan. Zero-based budgeting dan reserve tetap berlaku. |
| --- | --- |

|  | MEASUREMENT TicketNotifyIntent dan TicketIntent adalah sinyal intent. TicketIntent tidak boleh disebut Purchase. Purchase/Admission hanya boleh dinyatakan jika ada data transaksi/attendance yang benar-benar dapat diverifikasi. |
| --- | --- |

Status dokumen: supersedes Meta Ads Operating Playbook v1.0 setelah v1.1 diserahkan kepada tim. Data cinema/seat menggunakan cinema booking 2.pdf sebagai source of truth terbaru.

00  START HERE — HALAMAN WAJIB BACA

Baca bagian ini sebelum membuat Campaign, Ad Set, atau Ad apa pun.

| HAL WAJIB DIPAHAMI | KEPUTUSAN OPERASIONAL |
| --- | --- |
| North Star | Movement toward paid theatrical admissions. |
| Paid role | Create demand + sense demand + convert ticket action + defend occupancy. |
| Market | Nasional. Cold audience tidak boleh membutuhkan pengetahuan WOKO. |
| Cold hero | Official Trailer dan cutdowns menjadi primary cold-acquisition source mulai 19 Oktober. |
| Warm engine | WOKO familiarity, WOKO Journey, social engagers, roadshow proof, premiere proof. |
| Landing Page | Dipakai untuk action/intent. Tidak wajib untuk discovery/proof native Meta. |
| Primary intent pre-ticket | TicketNotifyIntent. |
| Primary intent ticket-live | TicketIntent. |
| Business truth | Ticket sold, sell-through, admissions, occupancy, screen/showtime capacity. |
| Budget | Rp100M maximum envelope; zero-based; reserve may remain unspent. |
| Roadshow | Sequential conversion laboratory: Preheat → Notify → Presale → TicketIntent → Screening → Proof. |
| Opening | Demand × capacity. Jangan membeli demand yang tidak dapat ditampung oleh layar/showtime. |

|  | DO NOT Jangan scale karena CTR murah. Jangan sebut TicketIntent sebagai Purchase. Jangan frame film sebagai “film WOKO”. Jangan terus beriklan ketika inventory hampir penuh. Jangan membagi budget rata demi fairness kota. Jangan menghabiskan reserve hanya agar budget terserap. |
| --- | --- |

01  SOURCE OF TRUTH + STATUS

Gunakan sumber terbaru; keputusan lama hanya berlaku jika tidak bertentangan.

| Sumber | Dipakai untuk | Status |
| --- | --- | --- |
| Campaign decisions sampai 6 Oct 2026 | Strategi paid, funnel, budget, native-vs-LP, presale architecture | CURRENT |
| cinema booking 2.pdf | Lokasi screening, cinema, seat, showtime, tanggal screening | CURRENT / latest |
| Daftar presale A–S dari produser | Tanggal buka presale city-by-city + national presale 10 Nov | CURRENT, kecuali screening date mengikuti cinema booking 2 |
| WOKO Analytics 28/90/365 | Starting audience/geo/behavior map; cut-off 11 Aug 2026 | REFERENCE |
| Meta Ads Operating Playbook v1.0 | Audit trail strategi sebelum update presale/seat/voucher/Rp100M | SUPERSEDED by v1.1 |

|  | WORKING RULE Jika ada konflik antara data cinema terbaru dengan jadwal lama, gunakan cinema booking 2.pdf untuk screening inventory. Tanggal presale tetap mengikuti daftar presale terbaru produser. |
| --- | --- |

02  STRATEGI YANG DIKUNCI

Hal ini tidak boleh diubah operator tanpa approval producer/campaign lead.

• Film adalah film nasional; WOKO = familiarity + ignition + warm mobilization, bukan market ceiling.

• Official Trailer = primary cold-acquisition source; jangan hanya boost trailer panjang, ekstrak creative families.

• ORGANIC MENEMUKAN BAHASA. PAID MEMPERBESAR BAHASA YANG TERBUKTI.

• PAID MEMBELI PERCEPATAN, BUKAN KEAJAIBAN.

• Native Meta dipakai ketika job iklan adalah FEEL/UNDERSTAND/PROOF; Landing Page ketika job-nya ACT/INTENT/TICKET.

• Views, reach, CPM, CTR, video completion = diagnostic; intent dan business truth memimpin scale decision.

• Zero-based budgeting: setiap rupiah harus mendapatkan alasan dari evidence.

• Roadshow bukan sekadar event tour; roadshow adalah sequential conversion laboratory sebelum national presale 10 Nov.

• Voucher harus menjadi measurable batch/source jika mekanisme redemption memungkinkan.

• Opening War = demand × capacity; scale hanya jika demand masih perlu dibangun dan supply masih tersedia.

• Reveal/spoiler dan religious-sensitivity guardrail tetap berlaku: joke the situation, never the faith.

03  MASTER PAID TIMELINE

19 Oktober menjadi National Paid Launch. 10 November menjadi National Conversion Switch.

| Tanggal/Window | Moment | Paid job | Primary signal |
| --- | --- | --- | --- |
| 19–21 Oct | Press Conference + Official Poster + Official Trailer | National cold acquisition + creative learning + Semarang ticket conversion | Native diagnostic + TicketNotifyIntent + TicketIntent Semarang |
| 22 Oct–9 Nov | Roadshow + special screening chain | National always-on + city preheat/presale/proof + warm pool growth | CPTI, sell-through, city sales pace, proof quality |
| 10–12 Nov | National presale opens 10 Nov + Gala 12 Nov | National ticket conversion + Notify retarget + proof production | TicketIntent + ticket velocity |
| 13–18 Nov | Final urgency | Reaction proof + showtime/cinema + warm conversion | CPTI + presale + remaining capacity |
| 19–22 Nov | National opening | Opening Geo Defense / occupancy | Admissions + occupancy + screen/showtime + intent |
| 23–26 Nov | Holdover / WOM | Only winning cities/screens + fresh WOM | Admissions trend + holdover capacity |

|  | TIMING NOTE Public roadshow/special screening pertama adalah Semarang 22 Oct. 20–21 Oct berfungsi sebagai launch aftermath, media/prep, ticket conversion, dan travel/field preparation. |
| --- | --- |

04  BUDGET ARCHITECTURE — RP100.000.000 MAXIMUM

Budget adalah working envelope. Allocation bukan spending obligation.

| Job | Window | Working envelope | Catatan |
| --- | --- | --- | --- |
| Official Trailer National Launch | 19–21 Oct | Rp10.000.000 | Cold national launch; trailer-derived acquisition; high-intent seeding |
| National Acquisition Always-On | 22 Oct–9 Nov | Rp10.000.000 | Continue national winners; warm pools; roadshow proof feeds national |
| Roadshow Special Screening Conversion | 19 Oct–8 Nov | Rp12.000.000 working | Initial city pool Rp8M; expandable by evidence; hard ceiling Rp15M incl. roadshow reserve |
| National Presale Launch | 10–12 Nov | Rp15.000.000 | National ticket conversion + Notify retargeting |
| Gala Proof + Final Urgency | 13–18 Nov | Rp18.000.000 | Audience proof, showtime, ticket urgency |
| Opening War | 19–22 Nov | Rp15.000.000 | Demand × capacity allocation; admissions-led reallocation |
| Holdover / WOM | 23–26 Nov | Rp5.000.000 | Fresh audience proof; only cities/screens with opportunity |
| Uncommitted Reserve | All period | Rp15.000.000 | Follow the winner; may remain unspent |

|  | RESERVE RULE Rp15M reserve tidak memiliki alamat di awal. Reserve dapat masuk ke Trailer, roadshow, national presale, final urgency, opening, atau tidak dibelanjakan jika evidence tidak mendukung. |
| --- | --- |

|  | ROADSHOW RULE Roadshow base working envelope Rp12M. Initial city launch pool Rp8M. City scale ceilings total Rp13.5M + central roadshow reserve Rp1.5M = hard roadshow ceiling Rp15M. Tambahan di atas Rp12M harus mengambil reserve dan membutuhkan evidence. |
| --- | --- |

05  CAMPAIGN ARCHITECTURE

Objective berada pada level Campaign. Setiap Ad memiliki job/behavior objective sendiri.

| Code | Campaign | Meta objective / optimization | Audience | Destination | Primary KPI |
| --- | --- | --- | --- | --- | --- |
| C01 | National Discovery / Creative Learning | Engagement / video-consumption equivalent when learning natively | Broad national + selective warm comparison | Native Meta | Creative diagnostic; NOT scale KPI |
| C02 | National Intent Acquisition | Traffic→LPV while event thin; then Sales/website conversion to active intent event when eligible/healthy | Broad national | Landing Page | Cost per Intent + Intent Rate |
| C03 | Warm Retargeting | Sales/website conversion to active intent event | Film engagers, video viewers, LPV, Notify, WOKO warm | Landing Page | Intent progression + Cost per Intent |
| C04 | Roadshow City Conversion | Traffic/LPV early or Sales/event-intent when signal adequate | City catchment + local warm + Notify | Landing Page | CPTI + sell-through + required sales pace |
| C05 | National Presale Conversion | Sales/website conversion to TicketIntent | Broad + warm + Notify + geo/cinema cells | Landing Page | CPTI + ticket velocity + sell-through |
| C06 | Opening Geo Defense | Sales/website conversion to TicketIntent | City/cinema/showtime opportunity cells | Landing Page | Admissions + occupancy + remaining capacity |

|  | PLATFORM NOTE Nama menu/objective Meta dapat berubah. Operator harus memilih ekuivalen UI yang memenuhi intent dokumen: native learning untuk discovery, LPV saat event masih tipis, dan website-event optimization ke active intent event ketika event eligible dan signal cukup. |
| --- | --- |

06  OBJECTIVE BY AD JOB

Ini menjawab “iklan ini dibuat untuk melakukan apa?” bukan hanya “objective apa di Ads Manager?”

| Ad job | Contoh creative | Campaign home | Destination | CTA | Success signal |
| --- | --- | --- | --- | --- | --- |
| Discovery | Official Trailer cutdown, comedy, romance, horror | C01 | Native Meta | Watch / engage ringan | Hold/completion + qualified engagement + brand linkage |
| High-intent acquisition pre-ticket | Winner derivative + date | C02 | Landing Page | Kabari saya | TicketNotifyIntent + cost/rate |
| Warm progression | WOKO/proof/romance → action | C03 | Landing Page | Kabari/Beli | Progression to intent |
| Roadshow preheat | City trailer/proof | C04 | Native or LP depending phase | Kabari saya | Notify + local warm pool |
| Roadshow ticket conversion | City/cinema card | C04 | Landing Page | Beli tiket / Pilih bioskop | TicketIntent + sell-through |
| National presale | Ticket available + winning film angle | C05 | Landing Page | Beli tiket | TicketIntent + ticket velocity |
| Premiere proof | Audience reaction | C01/C03 | Native first; LP derivative | Watch / Beli tiket | Proof quality + downstream intent |
| Opening showtime | City/cinema/showtime | C06 | Landing Page | Cari bioskop / Beli tiket | TicketIntent + admissions/occupancy |

07  AUDIENCE ARCHITECTURE

Satu market nasional, beberapa pintu masuk. Jangan mengunci cold national ke demografi WOKO.

| Audience cell | Pekerjaan | Creative door | Catatan |
| --- | --- | --- | --- |
| Broad National | Acquire people who do not need WOKO knowledge | High concept, comedy, romance, comedy-horror, theatrical scale | Default cold acquisition cell |
| WOKO Core / Lapsed | Reactivate + mobilize | WOKO familiarity, journey, character chemistry | Warm engine, not national identity |
| Warm Film | Progress interest | Trailer viewers, social engagers, LPV, proof viewers | Retarget with a NEW reason, not same ad |
| High Intent | Convert | Notify, LPV repeat, ticket-intent visitors | Priority when ticket live |
| Geo Roadshow | Fill special screening & sense local demand | City creative + ticket + proof | Use city catchment; scale by inventory need |
| Opening Geo | Defend occupancy | Showtime, local proof, ticket | Only where screens/seats still need demand |

08  MEASUREMENT FUNNEL

Semakin ke kanan semakin dekat ke business truth.

| Stage | Event/metric | Meaning | Decision use |
| --- | --- | --- | --- |
| Exposure | Impression / Reach / Frequency | Orang terekspos | Delivery diagnostic only |
| Attention | Video hold/completion / qualified engagement | Creative mendapat perhatian | Creative learning |
| Traffic | Landing Page View | Curiosity aktif sampai halaman | Traffic quality |
| Intent 1 | TicketNotifyIntent | Orang menyatakan ingin tahu saat tiket tersedia | Pre-ticket scale KPI |
| Intent 2 | TicketIntent | Orang menekan action menuju ticketing | Ticket-live scale KPI |
| Voucher | VoucherScan / VoucherRedeem | Activation intent / confirmed voucher conversion bila report tersedia | Offline attribution support |
| Ticket | Ticket sold / Sell-through | Purchase truth dari cinema/partner | Business validation |
| Cinema | Admission / Occupancy | Orang benar-benar datang | Opening truth + holdover decision |
| Advocacy | WOM / reactions / UGC | Audience menjual film kepada audience lain | Creative fuel |

|  | NON-NEGOTIABLE TicketIntent bukan Purchase. Jangan menghitung link click atau external ticket redirect sebagai transaksi. |
| --- | --- |

09  NATIVE META VS LANDING PAGE

Tidak semua Ads harus keluar dari Meta.

| Jika pekerjaan iklan adalah… | Destination | Contoh | Measurement |
| --- | --- | --- | --- |
| Membuat orang merasa / tertarik / memahami film | NATIVE META | Trailer cutdown, comedy, Mukidi×Sukma, soundtrack, reaction | Video/engagement diagnostic |
| Membangun social permission | NATIVE META | Roadshow crowd, premiere reaction, audience quote | Proof quality + downstream warm pool |
| Mendapatkan sinyal “kabari saya” | LANDING PAGE | Pre-ticket intent creative | TicketNotifyIntent |
| Mendorong beli/pilih bioskop/showtime | LANDING PAGE | Roadshow presale, national presale, opening | TicketIntent |
| Mengukur voucher / QR source | LANDING PAGE | Voucher QR city/activity/batch | VoucherScan → TicketIntent → Redeem |

|  | RULE FEEL → NATIVE. ACT → LANDING PAGE. |
| --- | --- |

10  LANDING PAGE SYSTEM

Bukan mini website perusahaan. Satu keputusan per state.

| Block | Wajib tampil | Tujuan |
| --- | --- | --- |
| Hero | Official poster/key visual, title, 19 Nov, commercial hook | Brand + date + premise comprehension in 2–3 seconds |
| Primary CTA | Kabari saya / Beli tiket / Pilih bioskop / Cari showtime | Conversion action |
| Trailer | Lightweight thumbnail/player; no heavy autoplay | Product proof for undecided users |
| Premise | 2–3 kalimat saja | Clarify product without long synopsis |
| Experience | Comedy + romance + supernatural + “Datang untuk ketawa…” | Why watch |
| Ticket/City | City, cinema, date, status, partner | Action path |
| Social Proof | Roadshow/premiere/opening reactions as available | Reduce hesitation |
| Sticky mobile CTA | Same primary action | Capture user after scroll |
| Footer | Official social, privacy/tracking disclosure | Trust + compliance |

|  | UX PRINCIPLE Landing page dibuat agar audience membuat satu keputusan, bukan menjelajahi perusahaan. Hindari navigation kompleks, splash screen, popup dini, dan video autoplay berat. |
| --- | --- |

11  LANDING PAGE STATES + INFORMATION

Satu master LP dapat berubah per fase dan per kota.

| State | Hero/Message | Primary CTA | Event | Extra blocks |
| --- | --- | --- | --- | --- |
| A — Pre-ticket | PIYE TO KIH? • 19 NOVEMBER DI BIOSKOP | KABARI SAYA SAAT TIKET TERSEDIA | TicketNotifyIntent | Trailer + premise + date |
| B — Roadshow Presale | [KOTA] • SPECIAL SCREENING • [DATE] | PILIH BIOSKOP / BELI TIKET | TicketIntent | Cinema cards + screening times + local proof |
| C — National Presale | TIKET 19 NOVEMBER SUDAH TERSEDIA | BELI TIKET | TicketIntent | City/cinema selector + Gala proof |
| D — Opening | SUDAH TAYANG HARI INI | CARI BIOSKOP & JAM TAYANG | TicketIntent | Audience proof elevated above trailer |
| V — Voucher | [KOTA] voucher landing state | LIHAT / KLAIM / BELI sesuai mechanic | VoucherScan / Claim / TicketIntent | Batch/source capture; redemption info |

Recommended mobile order: Hero → CTA → Trailer → Premise/Experience → Ticket/City → Social Proof → CTA repeat → Footer.

12  TRACKING + EVENT DICTIONARY

Pixel + CAPI + GA4 + UTM. Event names harus sedikit dan jelas.

| Event | Fire when | Core parameters | Business meaning |
| --- | --- | --- | --- |
| PageView | LP loads | source, campaign, city | Visit only |
| ViewContent | Meaningful LP content visible / qualified visit rule | creative_id, city, phase | Qualified LP consumption |
| TicketNotifyIntent | User confirms pre-ticket reminder intent | city, presale_type, creative_id, campaign_phase | High-intent pre-ticket signal |
| TicketIntent | User clicks toward official ticket path | city, cinema, presale_type, ticket_partner, creative_id | High-intent ticket action; NOT purchase |
| VoucherScan | Voucher QR/page entered | city, activity, voucher_batch | Offline activation response |
| VoucherClaim | Claim mechanic completed if used | city, voucher_batch | Stronger voucher intent |
| VoucherRedeem | Confirmed redemption report from system/partner | city, voucher_batch, ticket/order ref if allowed | Confirmed voucher conversion |

• Pixel + CAPI events should use the same event_id when both send the same user action, so deduplication is possible.

• UTM/source should persist through the LP where technically possible.

• Never send fake Purchase just to make Ads Manager look “more converted”.

• Privacy/tracking disclosure is mandatory on LP.

13  CREATIVE SYSTEM

Setiap creative mempunyai satu pekerjaan jelas.

| Code | Family | Audience | Format | Job | Destination |
| --- | --- | --- | --- | --- | --- |
| HC | High Concept | Cold national | 10–15s 9:16 + 4:5 | Premise comprehension | Native first → LP derivative |
| COM | Comedy Proof | Cold + warm | 10–20s 9:16 | Entertainment proof | Native; conversion derivative later |
| ROM | Mukidi × Sukma | Female / younger / non-WOKO | 15–20s 9:16 | Relationship attachment | Native → LP winner |
| HOR | Comedy-Horror | Category expansion | 10–15s 9:16 | Genre proof | Native → LP winner |
| THR | Theatrical Scale | Cold national / WOKO barrier | 10–15s 9:16 / 4:5 | “Ini film bioskop” proof | Native |
| WOK | WOKO Familiarity/Journey | WOKO core/lapsed | 10–30s vertical | Warm reactivation | Native → retarget LP |
| RDS | Roadshow Proof | Next city + national | 10–20s vertical | Crowd + local proof | Native; ticket CTA derivative |
| PRF | Premiere/Audience Proof | Warm + cold social permission | 8–20s vertical | Audience sells to audience | Native + LP retarget |
| NTF | Ticket Notify | High intent pre-ticket | Static/motion 4:5 & 9:16 | Create Notify pool | Landing Page → TicketNotifyIntent |
| TKT | Ticket/Showtime | Presale / opening | Static/motion/carousel | Direct conversion | Landing Page → TicketIntent |

|  | CREATIVE FORMAT RULE Default Reels/Stories production = 9:16, audio on, key message/title/CTA inside safe zone. Feed = 4:5. Gunakan placement asset customization; jangan mengandalkan auto-crop 16:9 sebagai sistem utama. |
| --- | --- |

14  19–21 OCT — OFFICIAL TRAILER NATIONAL LAUNCH

Rp10M working ceiling; jangan otomatis habis.

| FIELD | RULE |
| --- | --- |
| Job | Memulai national paid acquisition dengan film-first product proof. |
| C01 Discovery | Test trailer-derived families natively: HC, COM, ROM, HOR, THR. |
| C02 Intent | Bawa winning derivatives ke LP untuk TicketNotifyIntent. |
| Semarang overlap | Parallel city conversion: ticket sudah live untuk special screening 22 Oct. |
| Working launch pressure | Mulai sebagian budget pada 19 Oct; scale hanya winner 20–21 Oct. |
| Output yang dicari | 3–5 creative families yang layak dibawa ke national always-on dan roadshow derivatives. |

| Creative test | Cold job | Warm job | CTA when LP derivative |
| --- | --- | --- | --- |
| High Concept | Premise clarity | Remind/expand | Kabari saya |
| Comedy | Entertainment proof | Re-engage WOKO | Kabari saya |
| Mukidi×Sukma | Romance/female expansion | Deepen attachment | Kabari saya |
| Comedy-Horror | Category expansion | Genre proof | Kabari saya |
| Theatrical Scale | Cinema-value proof | Break “YouTube episode” barrier | Kabari saya |

15  ROADSHOW FLIGHTING MODEL

Setiap city menjalankan mini funnel yang sama.

| Stage | Timing | Creative | Destination | CTA | Primary read |
| --- | --- | --- | --- | --- | --- |
| PREHEAT | D-5 sampai presale-1 | Trailer/proof city version | Native; LP if Notify desired | Kabari saya | Warm pool + Notify |
| PRESALE OPEN | Ticket live day | Motion/static ticket + cinema card | LP | Beli tiket / Pilih bioskop | TicketIntent + first 24h sell-through |
| INTENSIFY | D-2 sampai D-1 | Urgency + proof + cinema detail | LP | Amankan kursimu | Required sales pace vs actual velocity |
| D0 | Screening day | Last availability only if seats remain | LP | Cek kursi | Remaining inventory |
| PROOF | D0 night–D+2 | Reaction/crowd/cast | Native first | Watch / next city | Proof quality + national lift |

|  | RULE Jangan promosi scarcity palsu. “Kursi terbatas / hampir habis” hanya boleh dipakai jika inventory report mendukung. |
| --- | --- |

16  ROADSHOW INVENTORY ECONOMICS

Ads roadshow mengisi inventory nyata. Gunakan rumus berikut dalam setiap city decision.

| Equation | Formula | How to use |
| --- | --- | --- |
| Gross Capacity | Seat per show × number of showtimes | Starting inventory from cinema booking |
| Sellable Capacity | Gross − comp/invitation/blocked seats | Denominator bisnis yang benar |
| Remaining Seats | Sellable − tickets sold | Pekerjaan demand yang masih tersisa |
| Sell-through | Tickets sold ÷ sellable capacity | How full the screening is |
| Required Daily Pace | Remaining seats ÷ days remaining | How many tickets/day must still sell |
| CPTI | Meta spend ÷ TicketIntent | Paid efficiency near ticket action |
| Intent-to-Seat | TicketIntent ÷ remaining seats | Demand pressure vs remaining inventory |
| Voucher Redemption Rate | Voucher redeemed ÷ voucher distributed | Offline activation efficiency |

|  | GROSS INVENTORY Latest roadshow file = 24 cinema entries / 17 markets / approx. 7,554 gross seats before comp/guest/blocked seats are removed. |
| --- | --- |

| Roadshow paid spend | Gross seats | Spend per gross seat capacity |
| --- | --- | --- |
| Rp8,000,000 initial city pool | 7,554 | ≈ Rp1,059 |
| Rp12,000,000 base working envelope | 7,554 | ≈ Rp1,589 |
| Rp15,000,000 hard roadshow ceiling | 7,554 | ≈ Rp1,986 |
| Rp20,000,000 illustration only | 7,554 | ≈ Rp2,648 |
| Rp40,000,000 illustration only | 7,554 | ≈ Rp5,295 |

|  | IMPORTANT Spend per gross seat capacity bukan CPA ticket. Angka ini hanya inventory pressure ratio agar tim memahami skala budget dibanding jumlah seat yang harus diisi. |
| --- | --- |

17  ROADSHOW CITY OPERATING MATRIX

Presale dates from producer list; screening inventory from cinema booking 2.pdf.

| City | Presale | Screen | Cinema | Gross | Initial | City cap | Audience emphasis | Creative emphasis |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Semarang | 19 Oct | 22 Oct | The Park XXI; Cinépolis Java Mall | 723 | Rp0.80M | Rp1.30M | 55% cold / 30% warm / 15% intent | Trailer premise + comedy; carousel 2 cinema |
| Jogja | 20 Oct | 23 Oct | Ambarrukmo XXI; Jogja City Mall XXI | 513 | Rp0.55M | Rp0.90M | 65% cold / 20% warm / 15% intent | Mukidi×Sukma + high concept; carousel 2 cinema |
| Magelang | 21 Oct | 24 Oct | Platinum Artos Mall; The Aloon-Aloon XXI | 300 | Rp0.30M | Rp0.55M | 60% cold / 25% warm / 15% intent | Comedy + “nonton lebih dulu”; carousel 2 cinema |
| Solo | 22 Oct | 25 Oct | Solo Paragon XXI; Platinum Pakuwon Mall Solo Baru | 798 | Rp0.75M | Rp1.25M | 55% cold / 30% warm / 15% intent | Trailer film-first + WOKO comedy; carousel 2 cinema |
| Sragen | 23 Oct | 26 Oct | Platinum Plaza Atrium Sragen | 203 | Rp0.25M | Rp0.45M | 55% cold / 30% warm / 15% intent | Short comedy Reel + single-cinema motion ticket card |
| Ngawi | 24 Oct | 27 Oct | NSC Ngawi | 452 | Rp0.40M | Rp0.75M | 55% cold / 30% warm / 15% intent | WOKO familiarity + comedy proof + ticket end-card |
| Madiun | 25 Oct | 28 Oct | CGV Plaza Lawu; Suncity Madiun XXI | 944 | Rp0.90M | Rp1.50M | 55% cold / 25% warm / 20% intent | High concept + comedy; carousel 2 cinema; strongest conversion test |
| Ponorogo | 26 Oct | 29 Oct | Cinépolis Ponorogo City Center | 244 | Rp0.30M | Rp0.50M | 55% cold / 30% warm / 15% intent | Javanese joy/comedy + local event relevance |
| Nganjuk | 27 Oct | 30 Oct | Sam's Studio Nganjuk | 214 | Rp0.25M | Rp0.40M | 55% cold / 30% warm / 15% intent | Direct 6–10s ticket motion + comedy hook |
| Mojokerto | 28 Oct | 31 Oct | CGV Sunrise Mall Mojokerto | 232 | Rp0.30M | Rp0.50M | 60% cold / 25% warm / 15% intent | Trailer cutdown + CGV ticket card |
| Gresik | 29 Oct | 1 Nov | Gressmall XXI | 165 | Rp0.25M | Rp0.45M | 60% cold / 25% warm / 15% intent | Single-cinema direct-response; hard stop cepat bila filling bagus |
| Surabaya | 30 Oct | 2 Nov | Royal XXI | 324 | Rp0.50M | Rp0.80M | 50% cold / 35% warm / 15% intent | High concept + theatrical scale + WOKO familiarity |
| Sidoarjo | 31 Oct | 3 Nov | Platinum Suncity Mall; Ciplaz Sidoarjo XXI | 546 | Rp0.50M | Rp0.90M | 55% cold / 30% warm / 15% intent | Comedy + group moviegoing; carousel 2 cinema |
| Malang | 1 Nov | 4 Nov | Dieng XXI; Cinépolis Town Square Malang | 414 | Rp0.50M | Rp0.80M | 55% cold / 30% warm / 15% intent | Mukidi×Sukma + comedy-horror; carousel 2 cinema |
| Kediri | 2 Nov | 6 Nov | Ciplaz Kediri XXI (Home Premiere) | 512 | Rp0.50M | Rp0.80M | 50% cold / 35% warm / 15% intent | Home Premiere / pride + film proof; jangan hanya nostalgia |
| Blitar | 3 Nov | 7 Nov | CGV Blitar Square | 162 | Rp0.25M | Rp0.45M | 55% cold / 30% warm / 15% intent | Direct ticketing + strongest comedy cut |
| Tulungagung | 4 Nov | 8 Nov | Golden Theatre Tulung Agung | 808 | Rp0.70M | Rp1.20M | 50% cold / 35% warm / 15% intent | WOKO familiarity + high concept + strong urgency |

|  | CITY BUDGET LOGIC Initial allocations total Rp8M. City scale ceilings total Rp13.5M. Central roadshow reserve Rp1.5M creates Rp15M hard ceiling. Actual spend should stop early when seat inventory no longer needs demand. |
| --- | --- |

18  VOUCHER MEASUREMENT SYSTEM

Voucher adalah activation + attribution layer. Nilai/discount mechanic masih TBD.

| Step | Metric/Event | Minimum code/data |
| --- | --- | --- |
| 1. Distribute | Voucher Distributed | city + activity + batch |
| 2. Scan | VoucherScan | QR to city-aware LP |
| 3. Claim (optional) | VoucherClaim | claim mechanic if used |
| 4. Ticket action | TicketIntent | city + cinema + voucher batch + source |
| 5. Redeem | VoucherRedeem | partner/system confirmation |
| 6. Attend | Admission if available | cinema/attendance source |

Recommended batch examples: SMG-CAMPUS-01 • SMG-MALL-01 • JOG-CAMPUS-01. Batch code is the minimum; individual codes are stronger if operationally feasible.

|  | TBD BEFORE FINAL IMPLEMENTATION Voucher value, validity, whether special screening vs regular, batch vs unique code, redemption platform, and who returns the redemption report to campaign. |
| --- | --- |

19  10 NOV — NATIONAL PRESALE SWITCH

Roadshow learning becomes national conversion system.

| Audience | Message job | Creative | CTA |
| --- | --- | --- | --- |
| Broad National | Film + ticket now available | Best trailer-family winner + ticket end-card | Beli tiket |
| Warm Film | Convert known interest | Proof + ticket urgency | Beli tiket |
| TicketNotifyIntent | Close high intent | “Tiket sudah dibuka” without creepy wording | Beli tiket |
| WOKO Warm | Mobilize core without narrowing film | Familiarity + national milestone + ticket | Beli tiket |
| Geo/Cinema Cells | Move demand to available inventory | City/cinema/showtime | Pilih bioskop |

|  | 10 NOV RULE From this point, primary paid KPI shifts to TicketIntent and ticket velocity. Keep discovery alive only where it still feeds incremental audience, not for vanity reach. |
| --- | --- |

20  12 NOV GALA → 13–18 NOV FINAL URGENCY

Gala is a paid creative production day, not only an event.

• Capture 5–8 short vertical reactions: non-WOKO, women, couples, comedy response, emotional surprise, media/public figure if rights are valid.

• Turnaround: same night / next morning. Reaction proof must enter ads while social permission is fresh.

• Warm retargeting should use proof + ticket urgency, not repeat the same trailer.

• Creative becomes more utilitarian as release approaches: city, cinema, showtime, 19 Nov, CTA.

| Creative | Cold role | Warm role | Destination |
| --- | --- | --- | --- |
| Audience reaction | Social permission | Close hesitation | Native first / LP derivative |
| Quote static | Fast proof | Reminder | Native / LP |
| Showtime card | Local conversion | Direct action | LP |
| Countdown | Urgency | Direct action | LP |

21  19–26 NOV — OPENING WAR + HOLDOVER

Paid becomes distribution-aware: demand must follow capacity.

| Demand | Capacity | Action | Reason |
| --- | --- | --- | --- |
| High | High | SCALE | Demand exists and inventory can absorb it |
| High | Low | REDUCE / REDIRECT | Do not buy demand that cannot be seated |
| Low | High | CONVERSION INTERVENTION | Use proof, showtime, local urgency; test if demand can be moved |
| Low | Low | EXIT / LOW PRIORITY | Weak opportunity; protect reserve |

|  | OPENING BUSINESS TRUTH TicketIntent helps sense demand, but admissions/occupancy/screen-showtime availability decide whether budget should stay, scale, or move. |
| --- | --- |

22  SCALE / HOLD / RE-EDIT / KILL

Decision harus membaca efficiency + downstream quality + inventory opportunity.

| Decision | Use when | Action |
| --- | --- | --- |
| SCALE | Cost per Intent at/above desired quality vs rolling baseline; Intent Rate healthy; seats still need demand; sales pace insufficient | Increase typically +20–30% per 24h; log reason |
| HOLD | Efficiency healthy; required sales pace on track; no urgent opportunity | Keep budget; observe next review window |
| RE-EDIT | Attention/LPV good but Intent Rate weak; message curiosity > buying intent | Keep winning hook; change proof, CTA, ticket clarity, sequence |
| KILL | Attention weak + intent weak after sufficient delivery; no strategic learning value | Stop and reallocate |

|  | MINIMUM EVIDENCE Do not kill or scale based on a handful of events. Use 24–72h review windows or adequate event volume; the exact minimum evolves with account baseline. |
| --- | --- |

23  CITY STOP / SCALE RULE

Roadshow conversion must stop when the business job is already done.

| Condition | Working decision |
| --- | --- |
| Sell-through <60% | Read days left + sales velocity + CPTI. Scale only if required pace is not being met. |
| Sell-through 60–85% | Usually HOLD / selective scale. Compare projected pace with remaining inventory. |
| Sell-through ≥85% + velocity healthy | REDUCE. |
| Sell-through ≥95% or remaining seats ≤10% | HARD STOP conversion spend unless new inventory/showtime opens. |
| CPTI cheap but screening nearly full | STOP/REDUCE anyway; cheap intent is no longer the business need. |
| CPTI slightly higher but many seats remain + pace weak | May SCALE if downstream ticket movement improves. |

24  PURCHASE LIKELIHOOD / DEMAND FORECASTING

Do not invent conversion probability before roadshow data exists.

Roadshow is the calibration dataset. After the first 4–6 markets, compute empirical low/base/high ranges using actual funnel and ticket data.

| Observed ratio | Formula | Use |
| --- | --- | --- |
| LPV → Notify | TicketNotifyIntent ÷ LPV | Pre-ticket intent quality |
| Notify → TicketIntent | TicketIntent from notify cohort ÷ Notify | Progression after ticket opens |
| LPV → TicketIntent | TicketIntent ÷ LPV | Ticket action rate |
| TicketIntent ↔ Ticket Sold association | Total ticket sold compared with TicketIntent trend | Association only unless partner attribution exists |
| Voucher Scan → Redeem | VoucherRedeem ÷ VoucherScan | Stronger attributable conversion where codes are tracked |
| Sell-through curve | Tickets sold ÷ sellable capacity over time | Forecast fill probability / pressure need |

|  | FORECAST LANGUAGE Use LOW / BASE / HIGH estimate and label it ESTIMATED. Do not say “Meta generated X purchases” without verified attribution. |
| --- | --- |

25  DAILY DASHBOARD + PRODUCER VIEW

One dashboard must combine Meta + ticket + cinema + voucher.

| Layer | Fields |
| --- | --- |
| Spend | Today / cumulative / campaign / city |
| Delivery | Reach / impressions / frequency / CPM |
| Attention | Hold / completion / qualified engagement / creative winner |
| Traffic | LPV / Cost per LPV |
| Intent | TicketNotifyIntent / TicketIntent / rates / costs |
| Voucher | Distributed / scans / claims / redeems / redemption rate |
| Ticket | Sellable / sold / remaining / sell-through / velocity |
| Cinema | Screen / showtime / seat capacity / occupancy |
| Business | Admissions / opening movement / holdover |
| Decision | Scale / Hold / Re-edit / Kill / Stop City |

|  | REPORTING RULE Ads Manager alone is not the source of truth. Advertiser must receive ticket/inventory updates from distribution/cinema and record decisions in Decision Log. |
| --- | --- |

26  DAILY SOP + WAR ROOM

Routine ringan sebelum opening; tighter cadence 13 Nov onward.

| Time/Cadence | Action |
| --- | --- |
| 09:00 | Read overnight spend, intent, ticket/sell-through, inventory. Flag city/creative requiring action. |
| Morning | Check tracking health, budget pacing, broken links, ticket status, comments/confusion. |
| 12:00 roadshow cities | Receive first ticket sold/remaining-seat update where possible. |
| 15:00 | Review creative fatigue, city movement, proof assets, capacity changes. |
| 20:00 roadshow cities | Second ticket update where possible; decide next-day city pressure. |
| 21:00 opening war | Lock overnight/next-day budget moves and content requests. |
| Every 24–48h | Scale/Hold/Re-edit/Kill. Avoid repeated setting edits without new evidence. |
| Every 72h | Reallocate between creative families, audiences, geos; update producer summary. |

27  ACCESS + GOVERNANCE

Operator mendapat kemampuan kerja; ownership tetap internal.

| Asset | Internal owner | Advertiser |
| --- | --- | --- |
| Facebook personal account | Private; never shared | No access |
| Business Portfolio | Full control; ideally ≥2 trusted internal owners | Limited access for role |
| Facebook Page | Internal full control | Task/partial access for Ads + Insights |
| Ad Account | Internal ownership/billing governance | Permission to build/manage/read performance |
| Instagram identity | Internal structural control | Use as ad identity if needed |
| Payment method | Producer/finance | No change rights unless assigned |
| Dashboard / Decision Log | Producer realtime visibility | Operate + document decisions |

• 2FA required for people with asset access.

• Never move ownership, delete Page, unlink/relink Instagram, or restructure Business Portfolio during campaign without approval.

• Major budget/objective/event/geo changes must be logged.

28  NAMING + UTM

Every ad must be traceable from Ads Manager to LP event and city decision.

| FIELD | FORMAT |
| --- | --- |
| Campaign | PTK_[PHASE]_[JOB]_[YYYYMMDD] |
| Ad Set | [AUDIENCE]_[GEO]_[EVENT/OPT] |
| Ad | [CREATIVE-CODE]_[ANGLE]_[FORMAT]_[VERSION] |
| UTM source | meta |
| UTM medium | paid_social |
| UTM campaign | campaign code |
| UTM content | creative/ad code |
| LP params | city, cinema, phase, presale_type when relevant |

Example: Campaign PTK_PH2_ROADSHOW_20261019 • Ad Set COLD_SMG_TICKETINTENT • Ad HC_Premise_9x16_V03.

29  CONTENT PRODUCTION SLA

Performance media needs fresh assets fast enough to affect the market.

| Asset | Deadline | Minimum output |
| --- | --- | --- |
| Official Trailer cutdowns | Before / same day 19 Oct | ≥5 families; 9:16 + 4:5 winners-ready |
| Roadshow proof | 2–6 hours after footage available | 1 Reel 9:16 + 1 Story + thumbnail/frame |
| Media proof | <24h after partner post live | Vertical cut or Partnership Ads candidate + quote static |
| Home Premiere | Night 6 Nov / morning 7 Nov | 3 reaction cuts + laughter montage + quote |
| Gala Premiere | Night 12 Nov / morning 13 Nov | 5–8 reaction cuts with diverse proof |
| Presale drop | Before ticket live | Static 4:5 + Story 9:16 + motion 6–10s + city derivatives |
| War Ticket | As soon as showtime confirmed | Modular city/cinema/showtime templates |
| Opening WOM | Daily | 2–4 fresh non-spoiler proof assets |

30  PRE-LAUNCH + CREATIVE QA CHECKLIST

No campaign launches until mandatory checks pass.

• Correct Business/Page/IG/Ad Account permissions tested.

• Payment method active; billing owner internal.

• Landing page mobile speed and ticket redirects tested.

• Pixel/CAPI/GA4 + event deduplication tested.

• UTM/source parameters visible and stored as designed.

• Correct city/cinema/screening date; no stale location data.

• Correct landing-page state: pre-ticket vs ticket-live vs opening.

• Creative job is clear: discovery/proof/intent/conversion.

• 9:16/4:5 versions ready; subtitles and safe zones checked.

• Reveal/spoiler and religion guardrails checked.

• CTA is truthful; no fake scarcity.

• Partner/media/music/talent rights cleared for paid use.

• Ticket sales/inventory reporting owner assigned.

• Decision Log and producer dashboard ready.

31  APPENDIX — ROADSHOW GROSS INVENTORY

Gross = seat × showtime. Replace with sellable seats as soon as comp/blocked data arrives.

| City | Gross seats | Share of 7,554 | Operational reading |
| --- | --- | --- | --- |
| Semarang | 723 | 9.6% | Large inventory |
| Jogja | 513 | 6.8% | Medium inventory |
| Magelang | 300 | 4.0% | Medium inventory |
| Solo | 798 | 10.6% | Large inventory |
| Sragen | 203 | 2.7% | Small inventory |
| Ngawi | 452 | 6.0% | Medium inventory |
| Madiun | 944 | 12.5% | Large inventory |
| Ponorogo | 244 | 3.2% | Small inventory |
| Nganjuk | 214 | 2.8% | Small inventory |
| Mojokerto | 232 | 3.1% | Small inventory |
| Gresik | 165 | 2.2% | Small inventory |
| Surabaya | 324 | 4.3% | Medium inventory |
| Sidoarjo | 546 | 7.2% | Medium inventory |
| Malang | 414 | 5.5% | Medium inventory |
| Kediri | 512 | 6.8% | Medium inventory |
| Blitar | 162 | 2.1% | Small inventory |
| Tulungagung | 808 | 10.7% | Large inventory |

Largest gross inventories: Madiun 944; Tulungagung 808; Solo 798; Semarang 723. Small inventories such as Blitar 162 and Gresik 165 may require very little paid conversion if organic/field demand is already strong.

32  APPENDIX — DECISION EXAMPLES

Examples are illustrative, not benchmark targets.

| Scenario | Data | Decision |
| --- | --- | --- |
| City nearly full | Sell-through 96%; CPTI cheap; 18 seats left | STOP city conversion. Cheap intent no longer creates value. |
| Seats remain / pace weak | Sell-through 35%; 2 days left; required pace 200/day; actual 80/day; CPTI near median | SCALE +20–30% and strengthen conversion creative. |
| Attention high / intent low | Video completion strong; LPV strong; TicketIntent Rate weak | RE-EDIT CTA/proof/ticket clarity; do not celebrate views. |
| High demand / low capacity opening | TicketIntent strong; shows mostly full | REDIRECT budget to nearby available screens or wait for added shows. |
| Low demand / high capacity opening | Occupancy weak; many shows | Use audience proof + local showtime + urgency; test conversion intervention. |

33  PLATFORM NOTES + REFERENCES

Platform behavior can change. Use official Meta equivalents that preserve the intent of this handbook.

• Meta for Business — Instagram & Facebook Reels Ads: Advantage+ placements, placement asset customization, 9:16/audio/safe-zone creative guidance.

• Facebook Help Center — About Facebook Page access: task access can operate Ads/Insights in business tools; full control can manage settings/access.

• Internal source — cinema booking 2.pdf: latest special-screening cinema/seat/showtime inventory.

• Internal source — WOKO Channel 28/90/365 Analytics, cut-off 11 Aug 2026: starting audience and geo map.

• Internal source — campaign decisions reconciled through 6 Oct 2026: Rp100M envelope, sequential roadshow presale, native-vs-LP, voucher measurement, national presale 10 Nov.

|  | FINAL OPERATING PRINCIPLE WOKO MEMBUKA PINTU. FILM HARUS MELAMPAUI PINTU ITU. UANG BERGERAK MENGIKUTI EVIDENCE, BUKAN KALENDER. |
| --- | --- |